## Community Services (hidden)
BCRM SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN 2022/2023 FINANCIAL YEAR
KPA 1 Basic Service Delivery
Priority Area | Strategic Plan Objective | Strategy | Indicator | Activity / Project | Measurement Source | Baseline | Q1 Deliverable Target | Q1 Evidence | Actual perfomance | Reason for Variation | Corrective measure | Annual Target | Custodian
Enviromental services | To ensure a well maintained clean and healthy environment by 2027 and beyond | By procuringTLB and skip trailer | Number of TLB procured | TLB procured | Quartely Reports | 0 | SCM Processs | Quartely Report | Target achieved | Procurement process at BID Adjudication committee | N/A | 1 TLB procured | Director Community Services
|  |  | Number of skip trailer procured | Skip trailer procured | Quartely Reports | 0 | SCM Processs | Quartely Report | Target not achieved | Validity date of quotations have expired. | Re-advertisement | 1 of skip trailer procured | Director Community Services
|  | By Ensuring a properly managed landfill site | Distance in Km of fence erected in Somerset East Landfill Site | Erection of a fence in Somerset East Landfill Site | Quartely Reports | Somerset East Landfill Site | N/A | N/A | n/a | n/a | n/a | 1.3 km of fence erected in Somerset East Landfill Site | Director Community Services
|  |  | % progress on the installation of weigh bridge | Installation of weigh bridge | Quartely Reports | 0 | N/A | N/A | N/A | N/A | N/A | 100% Installation of weigh bridge | Director Community Services
|  |  | % progress on the construction of a guardroom in Cookhouse | Construction of a guardroom in Cookhouse | Quartely Reports | 0 | N/A | N/A | N/A | N/A | N/A | 100% progress on the construction of a guardroom in Cookhouse | Director Community Services
Water Quality | To ensure a healthy water environment to improve human health by 2027 | By conducting water quality monitoring and education awareness programmes in the community | Number of bacteriological water samples and chemical water samples taken | Drinking water sampling | Quartely Reports | 87 bacteriological samples and 4 chemical analysis | 24 bacteriological samples and 1 chemical analysis | Laborary report | Target met-24 bacteriological samples and 1 chemical analysis | Chemical analysis done. | N/A | 96 bacteriogical water samples and 4 chemical water samples taken | Director Community Services
Fire and Disaster services | To ensure prevention and management of fire incidents to promote safety of the environment, properties and humans by 2027 and | By conducting fire safety and prevention inspections at commercial entities and public amenities | Number of fire prevention awareness programmes conducted | Conduct fire prevention awareness programme to schools and/or communities | Quartely Report submitted to Portfolio Committee, dated photos, attendance register & Program Report | 24 prevention awareness programmes to schools and communituies conducted | 6 prevention awareness programmes to schools and communities conducted | Attendance register, photos. | Target not met- 2 Prevention awareness conducted. | Not provided | not provided | 24 fire prevention awareness programmes conducted | Director Community Services
|  |  | Number of fire safety and prevention inspections conducted in commercial entities and public amenities | Conduct fire safety and prevention inspections in commercial entities and public amenities | Quartely Report submitted to Portfolio Committee, dated photos, attendance register & Program Report | 133 fire safety and preventions inspections conducted in commercial entities and public amenities | 30 fire safety and prevention inspections conducted in commercial entities and public amenities | Inspection report | Target met-51 fire safety and prevention inspections conducted in commercial entities and public amenities | N/A | N/A | 120 fire safety and prevention inspections conducted in commercial entities and public amenities | Director Community Services
Libraries Services | To promote a culture of learning amongst communities of BCRM by 2027 and beyond | By sourcing of funding for the extension of library in Pearston | Number of business plan developed | Develop business plan | Quartely Reports | 1 Library in Pearston | 1 business plan developed | Business plan | Funding approved, no need for business plan. | N/A | N/A | 1 business plan developed | Director Community Services
Traffic Services | To ensure that the road users comply with the roads and traffic laws by 2027 and beyond to ensure a safe environment by 2027 | By upgrading Vehicle Testing Station through procurement of vehicle testing machine | Number vehicle testing machine procured | vehicle testing machine procured | Quartely Reports | Existing vehicle testing machine | N/A | N/A | N/A | N/A | N/A | 1 vehicle testing machine procured | Director Community Services
|  |  | Number of DLTC upgraded | DLTC upgrade | Quartely Reports | DLTC | N/A | N/A | N/A | N/A | N/A | 1 DLTC upgraded | Director Community Services
Leave management | To understand the transformation of the minicipality's systems and policies by 2027 |  |  | Performance evaluation conducted per quarter | Quartely Reports | 1 performance evaluation conducted per quarter | 1 reports submitted on leave management based on leave audit report | Reports | Target not met |  |  | 4 reports submitted on leave management based on leave audit report | Director Community Services
Risk management |  |  | Number of reports submitted on risks addressed as per the strategic risk register | Risks addressed as per the strategic risk register | Quartely Reports | 0 | 1 report | Reports | Target not met |  |  | 4 reports | Director Community Services
Internal Audit plan |  |  | Number of reports submitted on the implementation of Audit Action plan | Implementation of Audit Action plan | Quartely Reports | 0 | 1 reports submitted on the implementation of Audit Action plan | Reports | Target not met |  |  | 4 reports submitted on the implementation of Audit Action plan | Director Community Services
Individual perfomance |  |  | Number of performance agreements signed with employees | Performance agreements signed with employees | Quartely Reports | 0 | Performance agreements signed with employees | Reports | Target not met |  |  | Performance agreements signed with employees | Director Community Services
|  |  | No of performance evaluation conducted per quarter | Performance evaluation conducted per quarter | Quartely Reports | 0 | 1 performance evaluation conducted per quarter | Reports | Target not met |  |  | 4 performance evaluation conducted per quarter | Director Community Services
Management |  |  | Number of management meetings held per quarter | Management meetings | Quartely Reports | 0 | 1 management meetings held per quarter | minutes and attendance register | Target met | N/A | N/A | 4 management meetings held per quarter | Director Community Services
|  |  | Number of departmental meetings held per quarter | Departmental meetings | Quartely Reports | 0 | 1 departmental meetings held per quarter | attendance register | Target met | N/A | N/A | 4 departmental meetings held per quarter | Director Community Services
Wasteful,irregular and unauthorised expenditure |  |  | % reduction on wasteful, irregular and unauthorised expenditure | Wasteful, irregular and unauthorised expenditure | Quartely Reports | 0 | 25% reduction on wasteful, irregular and unauthorised expenditure | Reports | Target not met |  |  | 100% reduction on wasteful, irregular and unauthorised expenditure | Director Community Services
Procurement plans |  |  | % progress on the implementation of procurement plans | Implementation of procurement plan | Quartely Reports | 0 | 100% progress on the implementation of procurement plans | Reports | Target not met |  |  | 100% progress on the implementation of procurement plans | Director Community Services

## Finance
MR NIGEL BRANDON DELO – DIRECTOR: FINANCE SERVICES (CFO)
DEPARTMENT : FINANCIAL SERVICES
REPORTING PERIOD : MIDTERM REPORT ( OCT-DEC 2022)
KPA | KPA Weight | Strategic Objective | Programme / | Project Weight | Key | Baseline | Annual target | Sept target | MOV | Actual performance | Reason for non performance | Corrective measure | Action plan | December target | MOV | Actual performance | Reason for non performance | Corrective measure | Action plan | PMS Comments
|  |  | Project |  | Performance
Indicator
Municipal Financial Viability and Management | 100% | To ensure that the municipality is maintaining its assets during the asset useful life cycles | Asset Management | 5% | Number of Asset Management plans developed | 2020/21 Asset register | 1 Asset Management Plan developed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  | Asset Management | 5% | Number of reports on the implementation of asset management plans | 2020/21 Asset register | 2 reports on the implementation of asset management plans | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | To ensure compliance with MFMA and SCM regulations pertaining to reporting | Supply chain management, Asset management & Stores Management | 5% | Number of quarterly reports on compliance with SCM Policies and Legislation | 4 x SCM compliance reports for 2022/23 | 4 SCM compliance reports submitted to Council | 1 x SCM compliance report submitted to Council | 1 x SCM compliance report | Target met.See attached SCM compliance report June 2022 | N/A | N/A | N/A | 1 x SCM compliance report submitted to Council | 1 x SCM compliance report | Target met:1 x SCM compliance report submitted to Council | N/A | N/A | N/A | N/A
|  | To ensure compliance with MFMA and DORA regulations pertaining to reporting by 2023 | Financial Management & Reporting | 5% | Number of Section 71 (IYR) reports submitted to NT, Council by the 10th of each month | 12 x section 71 reports for 2020/21 | 12 section 71 (IYR) reports submitted to NT, Council by the 10th of each month | 3 section 71 (IYR) reports submitted to NT, Council | section 71 reports | Target met.See attached section 71 Reports for June,July & August 2022 | N/A | N/A | N/A | 3 section 71 (IYR) reports submitted to NT, Council | section 71 reports | Target not met. 0 section 71 (IYR) reports submitted to NT | BTO staff still encountered alignment issues with SAMRAS budget schedules. | Solvem to be put on terms. | Solvem to be put on terms. | No time frames stated
|  |  |  | 5% | Number of quarterly financial reports submitted to Council within 30 days of the end of each quarter. | 4 x section 52 reports for 2022/23 | 4 quarterly financial reports submitted to Council within 30 days of the end of each quarter. | 1 quarterly financial report submitted to Council | section 52 report | Target met.See attached section 52 report June 2022 | N/A | N/A | N/A | 1 quarterly financial report submitted to Council | section 52 report | Target met.1 quarterly financial report submitted to Council | N/A | N/A | N/A | N/A
|  |  |  | 5% | Number of midyear financial reporting submitted to Council by 25 January 2023. | 2022/23 mid-year financial report | 1 midyear financial reporting submitted to Council by 25 January 2023. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | 5% | Number of adjustment budget submitted to PT; NT and Council by the 28th of February 2023 | Adjustment budget for 2022/23 | 1 adjustment budget submitted to PT: NT and Council by the 28th of February 2023 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | 5% | Number of draft budget by 31 March & final budget by 30 May for 2022/23 reports submitted to Council | Draft tabled budget for 2022/24, final tabled budget for 2022/24 | 1 draft budget by 31 March & 1 final budget by 30 May for 2023/24 reports submitted to Council | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | 10% | Number of financial statements submitted to the Auditor General by 31 August | 2020/21 Audited financial statements | 1 financial statement submitted to the Auditor General | 1 financial statement submitted to the Auditor General | 2021/22 draft financial statements | Target met.See attached Annual Financial Statements submitted to AG. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | 10% | % of capital budget spent on capital projects, and % of operational budget spent, measured as the total actual year to date capital expenditure / total approved capital budget x 100 for capital; measured as the total actual year to date operational expenditure / total approved operational budget | 2022/23 capital budget expenditure;2022/23 operational budget | 100 % of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100; 100 % of operational budget spent | 10% (Capital); | Section 71 Reports | Target partially met. Capital expenditure (9%) and Operational (25%) | Late implementation of projects and infrastructure water crisis | To liaise with bid committees and user departments on the implementation of projects | To liaise with bid committees and user departments on the implementation of projects by the end of October 2022. | 40% (Capital); | Section 71 Reports | Target not met. Capital Budget expenditure is at 29% and Operational Budget expenditure is at 48%. | N/a | N/A | N/A | Reasons and corrective measure not stated
25% (Operational)
|  |  |  | 5% | Sound financial management by maintaining an acceptable liquidity ratio | 2020/21 AFS | 1:0.92 or greater = liquidity ratio | 1:0.92 | Liquidity ratio | Target met Liquidity ratio 1:1.17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | 10% | Number of unqualified audit reports | 2021/22 unqualified audit report | 1 unqualified audit report | N/A | N/A | N/A | N/A | N/A | N/A | 2021/22 unqualified audit report | 1 unqualified audit report | Target met.1 unqualified audit report | N/A | N/A | N/A
|  | To ensure that the municipality is financially viable and that it can sustain its short-, medium- and long-term obligations to provide services to the community in a sustained manner by 2027 | Revenue Enhancement plan Review | 5% | No of Revenue Enhancement plan Reviewed | Revenue enhancement plan | 1 Revenue enhancement plan reviewed | N/A | N/A | N/A | N/A | N/A | N/A | Revenue enhancement plan | 1 Revenue enhancement plan reviewed | Target met.See attached revenue enhancement plan with minutes of meeting and attendance register. | N/A | N/A | N/A
|  |  |  | 10% | No of reports submitted on the Implementation of Revenue enhancement plan | 4 implementation reports on Revenue enhancement plan | 4 implementation reports on Revenue enhancement plan | 1 implementation report on Revenue enhancement plan | implementation report on Revenue enhancement plan | Target met.See attached implementation report on Revenue enhancecement Plan | N/A | N/A | N/A | 1 implementation report on Revenue enhancement plan | implementation report on Revenue enhancement plan | Target met.1 implementation report on Revenue enhancement plan | N/A | N/A | N/A
[5 empty] | No of progress reports on debtors collections | 4 progress reports on the debtors’ collections | 4 progress reports on the debtor collection rates | 1 progress report on the debtor’s collection | progress report on the debtors collection | Target met.See attached progres report. | N/A | N/A | N/A | 1 progress report on the debtor’s collection | progress report on the debtors collection | Target not met. | N/A | N/A | N/A | KPI not aligned with the approved SDBIP
|  |  |  | 5% | Number of cost-effective tariff plan developed | 1 cost tariff plan developed | 1 cost tariff plan developed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | 5% | Number of indigent registers updated | 4 indigent registers updated | 4 indigent registers updated | 1 indigent register updated | indigent register updated | Target met.See attached indigent register. | N/A | N/A | N/A | 1 indigent register updated | indigent register updated | Target met.1 indigent register updated | N/A | N/A | N/A | N/A

## Community Service (2)
DIRECTOR COMMUNITY SERVICES
DEPARTMENT : COMMUNITY SERVICES
Reporting period : Midterm Report (October -December 2022)
KPA | KPA Weight | Strategic Objective | Programme / | Project Weight | Key | Baseline | Annual target and Timeframe | Sept | MOV | Actual performance | Reason for non performance | Corrective measure | Action plan | Dec | MOV | Actual performance | Reason for non performance | Corrective measure | Action plan/Time froam
|  |  | Project |  | Performance
Indicator
Basic Service Delivery | 80% | To ensure a safe healthy environment to improve human safety and health by 2027 | Procurement of TLB | 10 | Number of TLB procured | 0 | 1 TLB procured | SCM Processs | Quartely Report | Target achieved | Procurement process at BID Adjudication committee | N/A | To procure 1 TLB | Procurement of TLB | Advertisement of the TLB | Target not met: Procurement of TLB was done | Procurement process are not yet finished | Make follow up until TLB IS Procured | Weekly follow ups
|  |  | Procurement of skip trailer | 10 | Number of skip trailers procured | 0 | 1 Skip Trailer procured | SCM Processs | Quartely Report | Target not achieved | Validity date of quotations have expired. | Re-advertisement | To procure Skip trailer | Procurement of Skip trailer | procurement process are not yet finished | Target not met: Procurement of Skip trailer was not done | Procurement process are not yet finished | Make follow up until Skip trailer is Procured | Follow up weekly.
|  |  | Erection of fence at Somerset East Landfill site | 10 | Distance of km of fence erected in SE Landfill site | Somerset East Landfill site | 1.3 km of fence erected in Somerset East Landfill site | N/A | N/A | n/a | n/a | n/a | To erect fence in Somerset East Landfill site | SCM Process | Minutes of bid Adjudication Committee | Target met : SCM Process were done | n/a | n/a | Follow up weekly.
|  |  | Installation of weigh bridge | 10 | % progress on the installation of weigh bridge | 0 | 100% Installation of weigh bridge | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  | Construction of a guardroom in Cookhouse | 10 | % progress on the construction of a guardroom in Cookhouse | 0 | 100% progress on the construction of a guardroom in Cookhouse | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  | Drinking water sampling | 10 | Number of bacteriological water samples and chemical water samples taken |  | 96 bacteriogical water samples and 4 chemical water samples taken | 24 bacteriological samples and 1 chemical analysis | Laborary report | Target met-24 bacteriological samples and 1 chemical analysis | Chemical analysis done. | N/A | 24 bacteriological samples and 1 chemical analysis | 24 bacteriological samples and 1 chemical analysis | Bacteriological samples, | Target not met -24 bacteriological samples and 0 chemical analysis | The department is still waiting for chemical analysis results | will be performed in Q3 | N/A
|  |  | Conduct fire prevention awareness programme to schools and/or communities | 5 | Number of fire prevention awareness programmes conducted | 24 prevention awareness programmes to schools and communituies conducted | 24 fire prevention awareness programmes conducted | 6 prevention awareness programmes to schools and communities conducted | Attendance register, photos. | Target not met- 2 Prevention awareness conducted. | Not provided | not provided | n/a | 6 prevention awareness programmes to schools and communities conducted | Attendance register, photos. | Target not met :4 prevention awareness programmes to schools and communities conducted | Prevention awareness programmes cancelled due to unrest and fire vihicles had mechanical faults. | Prevention awareness programmes will be conducted in Q3 | 2023-03-31
|  |  | Conduct fire safety and prevention inspections in commercial entities and public amenities | 5 | Number of fire safety and prevention inspections conducted in commercial entities and public amenities | 133 fire safety and preventions inspections conducted in commercial entities and public amenities | 120 fire safety and prevention inspections conducted in commercial entities and public amenities | 30 fire safety and prevention inspections conducted in commercial entities and public amenities | Inspection report | Target met-51 fire safety and prevention inspections conducted in commercial entities and public amenities | N/A | N/A | 30 fire safety and preventions inspections conducted in commercial entities and public amenities to be conducted | 30 fire safety and preventions inspections conducted in commercial entities and public amenities were done | Registers and Photos | Target not met :25 fire safety and preventions inspections conducted in commercial entities and public amenities were done | n/a | n/a
|  |  | Develop business plan | 5 | Develop business plan | 1 Library in Pearston | 1 business plan developed | 1 business plan developed | Business plan | Funding approved, no need for business plan. | N/A | N/A | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  |  | Vehicle testing machine procured | 3 | Vehicle testing machine procured | Existing vehicle testing machine | 1 vehicle testing machine procured | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | n/a | The KPI be moved to the next financial year | n/a
|  |  | DLTC upgrade | 2 | Number of DLTC upgraded | DLTC upgrade | 1 DLTC upgraded | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | n/a | The KPI be moved to the next financial year | N/A
Instirutional Development | 15% | To understand the transformation of the minicipality's systems and policies by 2027 | Leave management | 2 | No of reports submitted on leave management based on leave audit report | Leave management | 4 reports submitted on leave management based on leave audit report | 1 reports submitted on leave management based on leave audit report | Reports | Target not met |  |  |  | 1 reports submitted on leave management based on leave audit report | Reports | Target not met |  |  | Reasons and corrective measure not stated
|  |  | Risk management | 2 | No of reports submitted on risks addressed as per the strategic risk register | Risk management | 4 report | 1 report | Reports | Target not met |  |  |  | 1 report | Reports | Target not met |  |  | Reasons and corrective measure not stated
|  |  | Internal Audit plan | 2 | No of reports submitted on the implementation of Audit Action plan | Implementation of Audit Action plan | 4 reports submitted on the implementation of Audit Action plan | 1 reports submitted on the implementation of Audit Action plan | Reports | Target not met |  |  |  | 1 reports submitted on the implementation of Audit Action plan | Reports | Target not met |  |  | Reasons and corrective measure not stated
|  |  | Individual perfomance | 2 | No of performance agreements signed with employees .No of performance evaluation conducted per quarter |  | Performance agreements signed with employees | Performance agreements signed with employees | Reports | Target not met |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a
[5 empty] | No.performance evaluation conducted per quarter |  | 4 performance evaluation conducted per quarter | 1 performance evaluation conducted per quarter | Reports | Target not met |  |  |  | 1 performance evaluation conducted per quarter | Reports | Target not met |  |  | Reasons and corrective measure not stated
|  |  | Management | 4 | No of management meetings held per quarter |  | 4 management meetings held per quarter | 1 management meetings held per quarter | minutes and attendance register | Target met | N/A | N/A | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  |  |  | 3 | No of departmental meetings held per quarter |  | 4 departmental meetings held per quarter | 1 departmental meetings held per quarter | attendance register | Target met | N/A | N/A | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Financial Viability | 5% | To promote sound financial management | Wasteful,irregular and unauthorised expenditure | 3 | % reduction on wasteful, irregular and unauthorised expenditure |  | 100% reduction on wasteful, irregular and unauthorised expenditure | 25% reduction on wasteful, irregular and unauthorised expenditure | Reports | Target not met |  |  |  | 25% reduction on wasteful, irregular and unauthorised expenditure | Reports | Target not met |  |  | Reasons and corrective measure not stated
|  |  | Procurement plans | 2 | % progress on the implementation of procurement plans |  | 100% progress on the implementation of procurement plans | 100% progress on the implementation of procurement plans | Reports | Target not met |  |  |  | 100% progress on the implementation of procurement plans | Reports | Target not met |  |  | Reasons and corrective measure not stated

## Corporate Serv
BLUE CRANE ROUTE MUNICIPALITY
Mrs Novuko Kubone – Director Corporate Services
Corporate Services Department
Reporting period : Midterm Report (October -December 2022)
KPA | KPA Weight | Strategic Objective | Programme / | Project Weight | KPI | Baseline | Annual target | Sept | MOV | Actual performance | Reason for non performance | Corrective measure | Action plan /Time frame | December | MOV | Actual performance | Reason for non performance | Corrective measure | Action plan /Time frame | PMS Comments
Financial Viability | 5% | To ensure that the municipality is financial viable to sustain short, medium and long term obligations to be able to provide services to the community in a sustained manner by 2027 | Reviewal of rental agreements of municipal buildings | 1% | Number of municipal buildings rental agreements reviewed | R312 000 billed and R140 000 received | 8 municipal buildings rental agreements reviewed | 8 municipal buildings rental agreements reviewed | Report on reviewed lease agreements | Target met -11 lease agreements were reviewed. The report was tabled in the standing committee on 13 September 2022 and Exco on 22 September 2022. Recommendations were made for Council consideration and approval. | n/a | v | More agreements still need to be reviewed. Council still needs to approve the changes in the tarifs and the increase of rent. | Monitor lease agreements | Report on leases on municipal properties | Target met : Lease report tabled to Council and approved. New lease agreements done (Annexure A - report on lease agreements ) | n/a | n/a | n/a | Evidence sufficient
|  |  | Thorough reporting and implementation of LGSETA Grant | 2% | % of increased revenue from LGSETA Grant | 0.5% is received from LGSETA, R339 777.83 received in 21/22 FY | 1% increased revenue from LGSETA Grant | Submit report to LGSETA on trainings conducted | Training report | Target met - report submitted to LGSETA on trainings conducted | n/a | n/a | n/a | Submit report to LGSETA on trainings conducted | Training Report | Target not met : Report submitted to LGSETA on trainings and an amount of R270 139.24 was disbursed by LGSETA to BCRM on 08 December 2022. (Annexure B - Training report and Letter from LGSETA) | n/a | n/a | n/a | Reason and corrective ,measure not submitted
|  |  | Procurement plan implementation | 1% | % progress on the implementation of procurement plans | 100% | 100% progress on the implementation of procurement plans | 100% progress on the implementation of procurement plans | Report | Target not met - No evidence on the file .Computer equipment was procured (5 laptops for Management). | Procurement Plan was received after July and so no procurement was done in July | n/a | Procurement plan be adopted with the budget | 100% progress on the implementation of procurement plans | Report | Target met : 100% progress on the implementation of procurement plans | No bidders for the two-way radios | Re-advertisement of the tender | 2023-03-31 | N/a
|  |  | Wasteful, Irregular & Unauthorised expenditure | 1% | % reduction on wasteful, irregular and unauthorised expenditure | 100% | 100% reduction on wasteful, irregular and unauthorised expenditure | 25% reduction on wasteful, irregular and unauthorised expenditure | Report | Target not met - No evidence on the file .No wasteful, irregular and unauthorised expenditure contributed by Corporate Services | n/a | n/a | n/a | 100% reduction on wasteful, irregular and unauthorised expenditure | 50% reduction on wasteful, irregular and unauthorised expenditure | Target not met:0% reduction on wasteful, irregular and unauthorised expenditure | SCM report indicated that the SLA with Royal Security does not have a clause on Performance Monitoring although Meetings with Royal Security have been taking place with regards to their service and challenges. The Irregular expenditure still remains the same. (Annexure D - Procurement Plan and Minutes of meetings with Royal Security). | New SLA with the new SP will be entered into. | n/a | N/a
Basic Service Delivery | 10% | To provide strategic support to the community in order to assure a world class operating citizenry by 2027 | Career Expo | 5% | Number of Career expo for Grade 12 learners coordinated | No career pathing opportunities offered by BCRM | 1 Career expo for Grade 12 learners coordinated | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | N/a
|  |  | Career pathing opportunities | 5% | No of young people workshopped on job application processes | No career pathing opportunities offered by BCRM | 30 young people workshopped on job application processes | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | N/a
Institutional Development & Transformation | 73% | To undertake the transformation of the Municipality’s systems and policies across the board by 2027 | Policy Reviewal | 6% | Number of HR Policies reviewed | 23 HR Policies | 6 HR Policies reviewed (Leave management ,Dress code ,Uniform & PPE ,Labour Relations, Individual PMS and Employment policy) | 4 HR Policies reviewed (Leave management policy ,Dress code ,Uniform & PPE policy and Individual PM policy) | report on reviewed HR Policies | Target not met -2 Policies (Leave management policy and Dress code ,Uniform & PPE policy) were reviewed, tabled to Standing Committee and Exco. They will be tabled in the LLF then Council for adoption in Q.2 | Individual PM policy could not be completely reviewed as it has to be aligned with the Staff Regulations | Individual PM policy be reviewed. The number of policies to be reviewed be corrected to three (3) and not 4 in the SDBIP mid-term review. | 2022-12-31 | n/a | n/a | n/a | n/a | n/a | n/a | N/a
|  |  | HR strategies developed | 6% | Number of HR (CS) strategies developed |  | 3 HR Strategies developed ( HRMD, Business continuity and Section 14 PAIA manual ) | Develop draft HRMD, Business Continuity and Section 14 Manual | Council report | Target not met -1 Strategy developed which was supposed to be done in quarter 4 being the Section 14 PAIA manual | The other 2 strategies are still being researched and finetuned | 2 strategies be developed in quarter 2 | 2022-12-31 | Table final HRMD and Business Continuity Strategy to Council | Council report | Target not met :Section 14 Manual was adopted by Council on 31 October 2022. (Annexure F - Council Extract). HRMD and Business Continuity Strategies to be presented in Q3 | The other 2 strategies are still being researched and finetuned | 2 strategies be tabled to Council in Quarter 3 | 2023-03-01 | N/a
|  |  | Training and development of councillors | 5% | Number of councillors trained according to the WSP | 11 councillors trained | 11 councillors trained according to the WSP | 3 Cllrs Trained according to the WSP | Report and attendance register | Target met -11 Councillors workshoped by Cogta on 03 August 2022 on roles and responsibilities and governance. | n/a | n/a | n/a | 3 Cllrs Trained according to the WSP | Report and attendance register | Target not met : 5 Councillors trained by SALGA - LLF Training from 17 - 19 October 2022. (Annexure G - Attendance Register) | n/a | n/a | n/a | Evidence not sufficient ,Reason and corrective ,measure not submitted
|  |  | Training and development of employees | 5% | Number of employees trained according to the WSP | 11 employees trained | 40 employees trained according to the WSP | 10 Employees trained according to the WSP | Report and attendance register | Target not met . 9 Employees workshopped by Cogta on 03 August 2022 on roles & responsibilities and governance | SCM processes delayed in the request for quotations for the Horticulture and customer care trainings | Trainings will be done in Q.2 | 2022-12-31 | 5 Employees trained according to the WSP | Report and attendance register | Target not met : No employee was trained in Q.2 except that the TOR were submitted to SCM, Demand Management Form was filled, Requisition was done | Training advert came out in December 2022. | Appointment of service providers be completed in January 2023 | 2023-03-01 | N/a
|  |  | Employee Assistance Programme - Wellness | 5% | Number of Wellness Programme conducted | 2 wellness programmes (1 wellness day and 1 Prayer Day) | 1 Wellness Programme conducted (Partnership with AV Hospital, Wellness Campaign ) | n/a | n/a | 1 Nelson Mandela Day coordinated with the MEC for Finance & Economic Development on 28 July 2022. 1 wellness day (Cancer Awareness) held on 28 September in partnership with Andre Vosloo hospital. ( Target not applicable to the quarter) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  |  | Employee Relations Activities | 5% | Number of events coordinated | 2 Employee relations programmes (Policy roll-out and Superviser's workshop) | 1 event coordinated (Municipal Sports day) | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | N/a
|  |  | Coordinate functioning of HR Committees | 5% | Number of HR Committees coordinated | Statutory HR Committees have been established | 4 HR Committees sittings coordinated(LLF, Training\Employment Equity, OHS and Covid -19 ) | 6 | Agenda | Target met -LLF sat on 28 7.22, 31.8.22 , OHS sat on 11.8.22 & Covid-19 sat on 15.09.22 | Training&Employment Equity could not sit due to none availability of members. | Training\Employment Equity and Covid -19 committee to sit in Q.2 | 2022-12-31 | 4 HR Committees sittings coordinated(LLF, Training\Employment Equity, OHS and Covid -19 ) | Agenda | Target not met : 3 HR Committees sittings coordinated . LLF sat on 15 November 2022. Training & Employment Equity Committee sat on 10 November 2022. OHS Committee sat on 09 November 2022. Covid-19 Committee meeting sat on 15 September 2022. (Annexure H- Agenda for LLF, OHS, T&EE and Covid 19 meetings) | Covid-19 Committee did not sit as the pandemic has declined and there are no cases within the BCRM Jurisdiction and in the municipality | That target for sitting of Covid-19 Committee be reduced during the review of SDBIP | 2023-02-01 | N/a
|  |  | Individual performance management | 5% | Number of employees with performance agreements and plans developed | 7 employees from CS signed performance agreements | 14 employees with performance agreements and plans developed | 14 employees with performance agreements and plans developed | performance agreements and plans | Target not met .Done for 5 senior Management and 6 CS Staff that report directly to D: Corp Services | The target of 14 is incorrect | Target of 14 be corrected in the mid - term review of SDBIP | 2022-12-31 | n/a | n/a | n/a | n/a | n/a | n/a | N/a
|  |  | Performance Assessments | 5% | No of performance evaluation conducted per quarter | 0 | 4 performance evaluation conducted | 1 performance evaluation conducted per quarter | report, attendance register | Target not met - 0 performance evaluation conducted per quarter | n/a | n/a | n/a | 1 performance evaluation conducted per quarter | Report, attendance register | Target not met . | Q1 performance assessment will be done in conjunction with quarter 2No recording of quarter 1 individual assessments was done | Quarter 1 assessments be on record | 2023-03-01 | N/a
|  |  | Development of Municipal Newsletter | 5% | Number of internal Newsletters developed | 0 | 4 internal Newsletters developed | 1 internal Newsletter developed and distributed | Internal Newsletter | Target not met -The draft has not been tabled to Management as yet for approval | The draft be tabled to Management first | to be tabled to Management in Q2 | 2022-12-31 | 1 internal Newsletter developed and distributed | Internal Newsletter | Target not met -The draft has not been tabled to Management as yet for approval | The draft will be tabled to Management first | To be tabled to Management in Q3 | 2023-03-01 | n/a
|  |  | Installation of IT Infrastructure | 5% | Number of ICT Infrastructure installed | ICT Policies are in place but with no adequate budget for implementation | 1 ICT Infrastructure installed (Upgrade Server, Two- way radios, laptops for Councillors | Procurement of laptops for 6 Councillors | invoice and report | Target not met |  |  |  | Procurement of walkie talkie for Technical Services | invoice and report | Target met : Procurement of Two-way radios was advertised but no bidders tendered. Please refer to Annexure C2) | No bidders for the two-way radios | Re-advertisement of the tender | 2023-03-23 | N/a
|  |  | ICT policies | 6% | Number of ICT policies Reviewed | ICT Policies are in place | 4 ICT policies Reviewed | 2 ICT policies Reviewed (Telephone Management policy and ICT Strategy) | Report | Target met -Telephone Management policy and ICT Strategy were reviewed and tabled to ICT Steercom, Corporate Services Standing Committee and Exco. | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | N/a
|  |  | Leave Management | 5% | No of reports submitted on leave management based on leave audit report | 0 | 4 reports submitted on leave management based on leave audit report | 1 reports submitted on leave management based on leave audit report | Report | Target not met - no evidence submitted | n/a | n/a | n/a | 1 reports submitted on leave management based on leave audit report | 1 report | Target not met : Leave management done. Leave uploaded on SAMRAS and leave books reconciled with the system (Annexure J - Leave management report for Q2) | n/a | n/a | n/a | Evidence insufficent after the review by IA
|  |  | Corporate Services Department Meetings | 5% | No of departmental meetings held per quarter | 4 | 4 departmental meetings held per quarter | 1 departmental meetings held per quarter | report | Target met -Departmental meetings held on 01/08/2022, 11/08/2022; 05/09/2022 | n/a | n/a | n/a | 1 departmental meetings held per quarter | report | Target not met : 1 Departmental meetings held (Annexure K - Attendance register) | n/a | n/a | n/a | Evidence insufficent after the review by IA
Local Economic Development | 5% | To create a conducive environment for economic growth and job opportunities by 2027 | Coordination of Incubator Programme | 5% | Number of incubator programmes coordinated and completed | LED not fully visible within the municipality | 1 incubator programme plan developed for BCRM ( Pearston) | Develop plan for incubator programme on establishment of internet café in Pearston | Final Plan | Target not met -No evidence submitted .The draft plan has not been tabled to the Management for further inputs | Management meetings had to focus mainly on AG and so the attention had to be on AG items and the plan could not be tabled | present the plan to Management, Standing Committee, Exco and Council | 2022-12-31 | Solicit expression of interest from the youth of Pearston | Expression of interest advert and report | Target met : Concept was tabled to the CS Standing committee.Meeting with youth of Pearston to explain the concept was held on 14 November 2022. Advert was done and placed in Pearston. (Annexure L - Report; Incubator Concept; Meeting with Pearston youth poster and Incubator Programme advert and Application Form) | n/a | n/a | n/a | Evidence sufficient
Good Gov & Public Participation | 7% | To be a leading provider in rendering excellent customer services and maintain good relations with the community of Blue Crane Route Municipality by 2027 | Development of BCRM Customer Care Policy and Standard Service Charter | 3% | Number of Customer Care Services Policy developed | Inadequate visibility of customer care, no policy in place | 1 Customer Care Services Policy developed | Consultation of BCRM departments on Customer Care Policy and Standard Service Charter | Attendance Register and report | Target met -Customer Care and Standard Service Policy has been developed and the Consultation of employees (CS and Finance) began from 6 September 2022 | Consultation with the other 3 departments could not be done as the plan had to be on hold due to Customer Care Officer booked off sick. | Consultation with other departments be completed. Policy be presented to Standing committee, Exco and Council | 2022-12-31 | Draft Customer Care Policy and Standard Service Charter | Report to Council | Target met : Draft Customer Care policy and Standard Service Charter done and presented to Council on 25 November 2022 (Annexure M - Council report and extract on Draft Customer Care policy and Standard Service Charter) | n/a | n/a | n/a | N/a
|  |  | Establishment of Customer Care Centre | 2% | % progress on the establishment of Integrated customer care service center | Inadequate visibility of customer care, no policy in place | 20% progress on the establishment of Integrated customer care service center ( Plan for establishment of integrated customer care centre ) | n/a | n/a | n/a | n/a | n/a | n/a | 15% progress on the establishment of Integrated customer care service center (Plan for establishment of integrated customer care centre) | Council report | Target not met : Plan for establishment of integrated customer care centre not yet completed | Plan still has to be aligned properly with the Revenue enhancement strategy | Plan still has to be aligned properly with the Revenue enhancement strategy | 2023-03-31 | N/a
|  |  | Risk Management Register | 1% | No of reports submitted on risks addressed as per the strategic risk register | 0 | 4 | 1 report | Report | Target not met -No evidence submitted | n/a | n/a | n/a | 1 report submitted on the implementation of Strategic Risk Register for Corporate Services | 1 report | Target met :Report done (Annexure N - Report on Strategic Risk Register for Corporate Services) | n/a | n/a | n/a | N/a
|  |  | Audit Action Plan | 1% | No of reports submitted on the implementation of Audit Action plan | 0 | 4 reports submitted on the implementation of Audit Action plan | 1 reports submitted on the implementation of Audit Action plan | Report | Target not met -No evidence submitted | n/a | n/a | n/a | 1 report submitted on the implementation of Audit Action plan | 1 reports submitted on the implementation of Audit Action plan | Target not met :1 report submitted on the implementation of Audit Action plan (Annexure O - Report on Audit Action Plan) | n/a | n/a | n/a | Evidence insufficent after the review by IA

## Technical Services
Mr Ayanda Gaji – Director: Technical Services
Department: Technical Services
Reporting period : Midterm Report (October -December 2022)
KPA | KPA weight | Strategic Objective | Programme / | Project Weight | Key | Baseline | Annual target | Sept target | MOV | Actual Performance | Reason for non-performnace | Corrective measure | Action plan | December target | MOV | Actual Performance | Reason for non-performance | Corrective measure | Action plan | PMS Comments
|  |  | Project |  | Performance
Indicator
Basic Service Delivery | 60% | To ensure efficient, economical and quality provision of water and sewer services by 2027 | Upgrade Orange Fish Water Treatment Works | 15% | % progress on the upgrading Orange Fish Water Treatment Works | Orange Fish WTW | 100% progress on the upgrading Orange Fish Water Treatment Works | 30% progress on the upgrading Orange Fish Water Treatment Works | Site meeting reports and minutes & register and/or coordination meeting minutes & register | Target not met: 14% progress on the Upgrading Orange Fish Water Treatment Works. Activities that need to be done are: Raw water Inlet, Mixing Race, Settlers, Pipline is on progress, Fencing and Electrical Supply. | The contractor is behind on their program and cashflow problems and it seems they will not complete the contract on time. | Bosch projects has issued a contractual letter dated 16 September 2022 to the contractor for the slow progress and requested that they advise how they going to be measures in place to achieve completion. | Turn-around plan be submitted by contractor. PSP to issue site instructions or notices of poor performance. | 70% progress on the upgrading Orange Fish Water Treatment Works | Quarterly progress reports | Target not met: 70% progress on the Upgrading Orange Fish Water Treatment Works. Activities that need to be done are: Raw water Inlet, Mixing Race, Settlers, Pipline is on progress, Fencing and Electrical Supply. | N/A | N/A | N/A | Evidence not sufficient after the review by IA.
|  |  | Upgrading Cookhouse WTW | 10% | % progress on the upgrading of Cookhouse WTW | Cookhouse WTW | 100% Progress on the upgrading of Cookhouse water treatment works | Approval of ToR / Specification. | Demand form and draft ToR / Specification. | Target met: Approval of ToR / Specification was done, through signed demand form with specification. 0% Progress on the upgrading of Cookhouse water treatment works within 10 months. The project is currently at BAC. |  | N/A | N/A | 20% progress on the upgrading of Cookhouse WTW | Quarterly progress reports | Target not met: 22% Progress on site. The project has been delayed and also earmarked to be moved to 23/34 FY due to repriorization of funding emanating from partial approval of roll-over. | N/A | N/A | N/A | Evidence not sufficient after the review by IA.
|  |  | Upgraded sewer pumps | 2% | No of sewer pump stations in Somerset East upgraded | Five (5) sewer pump stations in Somerset East | 2 x no of sewer pump stations in Somerset East upgraded within 24 months | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | n/a
|  |  | Installed / equiped boreholes | 5% | No of boreholes augmented in Pearston | 4 boreholes augmented in Pearston | 2 boreholes augmented in Pearston within 12 months | N/A | N/A | N/A | N/A | N/A | N/A | 2 x no. of boreholes augmented in Pearston | Quarterly progress reports | Target not met: 0x no. of boreholes augmented in Pearston. The project is at bid committees (BEC & BAC), awaiting for the appointment of a contractor, since August 2022. | Prolonged procurement process due to engineer (BVI) not partaking in the bid committees as scheduled. | Email was written to BVI for poor perormance and to urgently sit for bid committees. | BAC set in December 2022 and refered the matter back to BEC. BEC will be sitting on the week of 16-20 Jan 23. | n/a
|  |  | Refurbished booster pumpstation | 5% | % progress on the refurbishment of Khanyiso waterpipe line and booster pumps | Exisiting booster pump station | 100% progress on the refurbishment of Khanyiso waterpipe line and booster pump within 8 months | N/A | N/A | N/A | N/A | N/A | N/A | 20% progress on the refurbishment of Khanyiso waterpipe line and booster pump | Quarterly progress reports | Target not met: 0% progress on site. Demand form, and tender documents, submited to SCM on the 30 November 2022, awaiting to be advertised. | Lack of As-Built drawings prolonged the compilation of tender document and now has been completed. Submission for advertisement done to SCM on the 30 November 2022, awaiting to be advertised. | SCM to expedite the advertisement. | PMU to register the project in the incoming MAC/DAC. SCM to advertise and shorten number of days and follow MFMA to the latter. Bid committees to sit promptly. | n/a
|  | To ensure quality electricity supply and reduction of Electricity losses by 2027 and beyond | Pearston Housing Development: Electricity demand analysis report | 2% | No of reports on the electrical assessment conducted in Millennium Park (Pearston) | Pearston housing development (11 houses) | 1 report on the electrical assessment conducted in Millennium Park (Pearston) | Approval of ToR / Specification.( Target not applicable as per the SDBIP) | Specification / ToR. | Target met: Approval of ToR / Specification was achieved, signed demand form with specification.( Target not applicable as per the SDBIP) | N/A | N/A | N/A | Appointment of PSP for assessment and/or electrical designs. | Quarterly progress reports | Target met: Service provider has been appointed and concept design report submitted. | N/A | N/A | N/A | Evidence sufficient
|  | To ensure that communities have access to reliable and efficient roads by 2027 and beyond | Paved gravel roads in Pearston | 2% | % Progress on the paving of gravel roads in Pearston | Exisitng gravel roads | 100% Progress on the paving of gravel roads in Pearston within 12 months | N/A | N/A | N/A | N/A | N/A | N/A | 10% Progress on the paving of gravel roads in Pearston | Quarterly progress reports | Target not met: 0% progress achieved in Pearston. Project is in planning stage. Material is delivered. Anticipating to commence 30 January 2023. | Delay in commencement on site by panel of contractors due to unresoveld issues between BCRM and the local SMMEs | Consultation has been done with respective SMMEs. Matter not resolved yet. | The project will be done in house. The municipality has started with the recruitment of labourers and procurement of material. The project will start in 30 January 2023 | n/a
|  |  | Paved gravel roads in Cookhouse | 2% | % Progress on the paving of gravel roads in Cookhouse | Exisitng gravel roads | 100% Progress on the paving of gravel roads in Cookhouse within 12 months. | N/A | N/A | N/A | N/A | N/A | N/A | 10% Progress on the paving of gravel roads in Cookhouse | Quarterly progress reports | Target not met: 0% progress achieved in Cookhouse. Project is in planning stage. Anticipating to commence 20 February 2023. | Delays in commencement on site by panel of contractors due to unresoveld issues between BCRM and the local SMMEs | Consultation has been done with respective SMMEs. Matter not resolved yet. | The project will be done in house. The municipality has started with the recruitment of labourers and procurement of material. The project will start in 30 January 2023. | n/a
|  |  | Paved gravel roads in Somerset East | 2% | % Progress on the paving of gravel roads in Somerset East | Exisitng gravel roads | 100% Progress on the paving of gravel roads in Somerset East within 12 months | N/A | N/A | N/A | N/A | N/A | N/A | 10% Progress on the paving of gravel roads in Somerset East | Quarterly progress reports | Target not met: 58% progress achieved in Somerset East (Carnation street & McKay street). Layer works have been completed, V-drains are 50% and edge beams are 65% | N/A | N/A | N/A | Evidence not sufficient
|  |  | Refurbished Mayila ,Memese and Glen Avon streets | 2% | % progress on the refurbishment of Mayila, Memese and Glen Avon streets | Existing surfaced road with bitumen | 50% progress on the refurbishment of Mayila , Memese and Glen Avon streets within 12 months | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Quarterly progress reports | N/A | N/A | N/A | N/A | n/a
|  |  | Conduct Environmental Impact Assessment process for stormwater drainage berm in Westview | 1% | % Progress on the Environmental Impact Assessment process for stormwater drainage berm in Westview | N/A | 100 % Progress on the Environmental Impact Assessment process for stormwater drainage berm in Westview within 8 months | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Quarterly progress reports | N/A | N/A | N/A | N/A | n/a
|  | To ensure that communities have access to well established social amenities by 2027 and beyond | Construct Aeroville sportsfield phase 2 | 10% | % progress on construction of Aeroville sportsfield phase 2 | Aeroville phase 1 | 100% progress on construction of Aeroville sportsfield phase 2 | 40% progress on construction of Aeroville sportsfield phase 2 | Site meeting, reports and minutes & register and/or coordination meeting minutes & register | Target met: 89% progress on construction of Aeroville sportsfield phase 2. Activities that need to be done are: Grassing 40mm sods, Supply and Install complete rugby field markings, Suppl and Install field marking markers complete as detailed. | N/A | N/A | N/A | 80% progress on construction of Aeroville sportsfield phase 2 | Quarterly progress reports | Target met: 100% progress on site. Practical completion was issued on November 2022. | N/A | N/A | N/A | Evidence sufficient
|  |  | Construct Westview sportsfields | 2% | % progress on construction of Westview sportsfields | N/A | 50% progress on construction of Westview sportsfields | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Quarterly progress reports | N/A | N/A | N/A | N/A | n/a
Institutional Development & Transformation | 5% | To build and strengthen the administrative and institutional capability of the municipality by 2027 | Signing of Performance Agreements by employyes reporting to the director | 1% | No. of performance agreement signed by employees reporting to the Director by 30 August 2021 | Existing plans and managers | 2x performance agreement signed by employees reporting to the Director by 30 August 2022 | 2x No. of performance agreement signed by employees reporting to the Director by 30 August 2022 | Signed perfomance agreement | Target not met: 1x No. of performance agreement signed by employees reporting to the Director by 30 August 2022 | Not provided | Not provided | Not provided | N/A | N/A | N/A | N/A | N/A | N/A | n/a
|  | To undertake the transformation of the Municipality’s systems and policies across the board by 2027 | Compiled and submitted reports on leave management | 0,5% | No. of reports submitted on leave management (oversight). | Leave books & SAMRAS | 4x No. of reports submitted on leave management (oversight). | 1x reports submitted on leave management (oversight). | Submitted leave management reports | Target met: 1x reports submitted on leave management (oversight). | N/A | N/A | N/A | 1x reports submitted on leave management (oversight). | Submitted leave management reports | Target met: 1x reports submitted on leave management (oversight). | N/A | N/A | N/A | n/a
|  |  | Compiled and submitted reports on strategic risk register | 0,5% | No of risk action plans implemented to address risks as per the strategic risk register. | Existing risk register | 4 no. risk action plans implemented to address risks as per the strategic risk register. | 1 no. of risk action plans implemented to address risks as per the strategic risk register. | Submitted strategic risk register reports | Target met: 1x reports submitted on leave management (oversight). This was the only action list on this quarter in the strategic risk register. | N/A | N/A | Turn-around plan be submitted by contractor. PSP to issue site instructions or notices of poor performance. | 1 no. of risk action plans implemented to address risks as per the strategic risk register. | Submitted strategic risk register reports | Target met: 1x reports submitted on leave management (oversight) and 1 x revenue enhancement strategy: energy optimisation. | N/A | N/A | N/A
|  |  | Compiled and submitted reports on Audit Action plan | 0,5% | No. of reports submitted on the implementation of Audit Action plan (IA and AG) | Existing Audit action plan | 4 x No. of reports submitted on the implementation of Audit Action plan (IA and AG) | 1 no. of reports submitted on the implementation of Audit Action plan (IA and AG) | Submitted audit action plan report | Q1 & Q2 to be removed as KPI not aligned with strategic plans of the municipality. Only Q3 & Q4 needs to be populated during mid-year |  |  |  | 1 no. of reports submitted on the implementation of Audit Action plan (IA and AG) | Submitted audit action plan report | Target not met: No reports compiled due to prolonged audit and management report outcomes. | The AGSA took time to conclude audit and this has ripple effect to the set target. | The target will be reviewed as it was not applicable for quarter 2, coincide with AGSA impending work. | Populate a webbase AIP on NT portal in quarter 3. | n/a
|  |  | Performance reviews conducted per employee | 0,5% | No of performance evaluation conducted per quarter | Performance reviews & Managers | 4 no. of performance evaluation conducted per quarter | N/A | N/A | N/A | N/A | N/A | N/A | 2 no. of performance evaluation conducted per quarter | Agenda, minutes & attendance register | Target not met: The new staff regulation was workshopped in November 2022. this target will be reviewed and implemented next FY. | Prolonged workshop on new staff regulations. | Workshop sessions and approval of PMS policy incoporating the new staff regulations. | This target will be reviewed and implemented next FY. | n/a
|  |  | Scheduling and held departmental meetings. | 1% | No of departmental meetings held per quarter | Available Staff | 4 no. of departmental meetings held per quarter | 1 x no. of departmental meetings held per quarter | Agenda, minutes & attendance register | Target met: 1 x no. of departmental meetings held per quarter for each section. | N/A | N/A | N/A | 1 x no. of departmental meetings held per quarter | Agenda, minutes & attendance register | Target met: 1 x no. of departmental meetings held per quarter. | N/A | N/A | N/A | n/a
|  |  | Reduced IUFW expenditure reports | 0,5% | % reduction on wasteful, irregular and unauthorised expenditure | MFMA and SCM regulations | 100% reduction on wasteful, irregular and unauthorised expenditure | 20% reduction on wasteful, irregular and unauthorised expenditure | MFMA section 71, 52(d), 72 and AFS. | Not reported |  |  |  | 40% reduction on wasteful, irregular and unauthorised expenditure | MFMA section 71, 52(d), 72 and AFS. | Target not met: 60% reduction on wasteful, irregular and unauthorised expenditure. Only 1x SP (JK Structures) for 2 invoices. | N/A | N/A | N/A | Reasons and corrective measure not stated
|  |  | Implemented procurement plans | 0,5% | % progress on the implementation of procurement plans | Exisiting procurement plans | 100% progress on the implementation of procurement plans | 20% progress on the implementation of procurement plans | Procurment plan, and Contract register | Not reported |  |  |  | 50% progress on the implementation of procurement plans | Procurment plan, and Contract register | Target not met: 56% progress on the implementation of procurement plans (Total tenders/FWQ is 34 and awarded is 19) | N/A | N/A | N/A | Evidence not sufficient after the review by IA.
Local Economic Development | 10% | To strive for reduction on household poverty by labour intensive construction methods by 2027 and beyond | Jobs created under EPWP | 10% | Number of jobs created through grant funding | Approved Grant | 230 jobs created through grant funding within 9 moths | 58 x Number of jobs created through grant funding | Request memorandum with list, signed contracts | Target met: 61 x Number of jobs created through grant funding | N/A | N/A | N/A | 30 x Number of jobs created through grant funding | Request memorandum with list, signed contracts | Target met: 40 jobs created through grant funding | N/A | N/A | N/A | Evidence not sufficient after the review by IA.
Financial Viability | 15% | To ensure compliance with MFMA and DORA regulations pertaining to reporting by 2022 | Monitoring compliance with MFMA & DORA check lists | 15% | % of capital budget spent on capital projects, and % of operational budget spent, measured as the total actual year to date capital expenditure / total approved capital budget x 100 for capital; measured as the total actual year to date operational expenditure / total approved operational budget | 2021/22 capital budget expenditure; and 2021/22 Operational expenditure | 100 % of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100; 100 % of operational budget spent within 12 months. | 10% of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100 and 10% of operational budget spent within 12 months. | MFMA Table C3: Financial Performance | Target met: 10% of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100 and 27% of operational budget spent within 12 months. | N/A | N/A | N/A | 40% of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100 and 30% of operational budget spent within 12 months. | MFMA Table C3: Financial Performance | Target not met: 32% of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100 and 50% of operational budget spent within 12 months. | N/A | N/A | N/A | Reasons and corrective measure not stated
Good Gov & Public Participation | 10% | To ensure that communities comply to building act and regulations by 2027 and beyond | Awareness campaigns conducted on building regulations | 2,5% | Number of awareness campaigns on building regulations conducted | Acts & Regulations | 4 awareness campaigns on building regulations conducted | Develop Flyers, Paphlets, and Banners( Target not applicable as per the SDBIP) | Created Flyers, Paphlets, and Banners. | Target met: Develop Flyers, Paphlets, and Banners. These were developed but not printed for awareness campaigns yet.( Target not applicable as per the SDBIP) | N/A | N/A | N/A | 2 x Number of awareness campaigns on building regulations conducted | Road show attendance registers | Target not met: There were no IDP/Budget roadshows done due to challenges experienced by MM and Mayors Office. | Budget constraints. | A reviewed schedule of roadshows to be done. | Roadshows to be done in the 3rd quarter and 4th quarter. | n/a
|  | To ensure that housing development status is achieved by 2027 and beyond | Compiled and submitted reports on needs register | 5% | Number of reports compiled on the housing needs register submitted to DHS | Housing national code and needs register system. | 4 reports compiled on the housing needs register submitted to DHS | 1x reports compiled on the housing needs register submitted to DHS | Housing needs register report compiled | Target met: Needs register report has been compiled. Applications per area / Town: Somerset East 3034, Cookhouse: 990 and Pearston: 666. | N/A | N/A | N/A | 1x report compiled of housing needs register and reporting to Council Structures. | Housing needs register report compiled | Target met: Needs register report has been compiled. Applications per area / Town: Somerset East 3045, Cookhouse: 990 and Pearston: 666. | N/A | N/A | N/A | n/a
|  | To ensure that SDF and LUMS is implemented to the latter by 2027 and beyond | Awareness campaigns conducted on SDF/LUMS | 2,5% | Number of awareness campaigns on SDF/LUMS conducted | Acts & Regulations | 4 Awareness campaigns on SDF/LUMS conducted | Develop Flyers, Paphlets, and Banners.( Target not aligned with the SDBIP) | Created Flyers, Paphlets, and Banners. | Target not met: Develop Flyers, Paphlets, and Banners. These were developed but not printed for awareness campaigns yet.( Target not aligned with the SDBIP) | N/A | N/A | N/A | 2 x Number of awareness campaigns on awareness campaigns on SDF/LUMS conducted | Road show attendance registers | Target not met: 3x awareness campaigns on SPLUMA, SDF & LUMS public participation was done with SBDM. | N/A | N/A | N/A | Evidence not sufficient

## MM
MUNICIPAL MANAGER
OFFICE OF THE MUNICIPAL MANAGER
REPORTING PERIOD: MIDTERM REPORT (OCT-DEC 2022)
KPA | KPA Weight | Strategic Objective | Programme / | Project Weight | Employee’s Activities | Key | Baseline | Annual target and Timeframe | Sept target | MOV | Actual Performance | Reason for non-performnace | Corrective measure | Action plan/Timeframe | December target | MOV | Actual Performance | Reason for non-performnace | Corrective measure | Action plan/Timeframe
|  |  | Project |  |  | Performance
Indicator
Institutional Development & Transformation | 5% | To undertake the transformation of the Municipality’s systems and policies across the board by 2027 | Leave management | 2% | Submit report on leave management based on leave audit report | No of reports submitted on leave management based on leave audit report | leave management report based on leave audit report | 4 reports submitted on leave management based on leave audit report | 1 report submitted on leave management based on leave audit report | leave management report based on leave audit report | Target met. Leave has been monitored for the employees in the department and a reconcillation is performed on a monthly basis. | Not Applicable | Not Applicable | Not Applicable | 1 report submitted on leave management based on leave audit report | leave management report based on leave audit report | Target met. Leave has been monitored for the employees in the department and a reconcillation is performed on a monthly basis. | n/a | Not Applicable | Not Applicable
|  |  | Individual Performance management | 1% | Sign performance agreements with employees | No of performance agreements signed with employees | 2 performance agreements | 2 performance agreements signed with employees | 2 performance agreements signed with employees | signed performance agreements with employees | Target met. Performance Agreements for Managers Internal Audit and PMS/IDP and PA: Municipal Manager have been signed. | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
|  |  |  | 1% | Conduct performance evaluation per quarter | No of performance evaluation conducted per quarter | 0 | 4 performance evaluation conducted per quarter | 1 performance evaluation conducted per quarter | Report | Not achieved. |  |  |  | 1 performance evaluation conducted per quarter | Report | Target not met.
|  |  | Management | 1% | Departmental meetings | No of departmental meetings held per quarter | 0 | 4 departmental meetings held per quarter | 1 departmental meetings held per quarter | Report | Not achieved. | Due to variuos official engagemets, externaly and internally incliding community unrests no formal meetings were held. | meetings will be convened in Q2 | Quarter 2 | 1 departmental meetings held per quarter | Minutes, Agenda and Attendacne Register | Target met. MANCO Meetings have been held in November and December 2022. | Not Applicable | Not Applicable | Not Applicable
Local Economic Development | 10% | To ensure promotion local economic development and job creation by 2027 and beyond | LED Unit | 2% | Establish LED Unit | No of LED unit established | 0 | 1 LED unit established | n/a | n/a | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Not Applicable
|  |  | LED Strategy | 2% | Developing LED strategy. | Number of Draft LED Strategy developed | 0 | 1 Draft LED Strategy developed | Not Applicable | Not Applicable | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Not Applicable
|  |  | Business forum | 1% | Business forum established | No of Blue Crane Route business forums established | 0 | 1 Blue Crane Route business forums established | Not Applicable | Not Applicable | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Not Applicable
|  | To facilitate the mainstreaming of Small, Medium and Micro Enterprises (SMMe's) business into the formal economy in BCRM by 2027 and beyon | SMME's | 2% | SMMe's support | Number of SMMe's supported | 6 | 9 of SMMe's supported ( CSD registration) | Not Applicable | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Not Applicable
|  |  | Investment Activites | 2% | Conduct Investment activities | Number of activities conducted for investment promotion | 0 | 1 activity conducted for investment promotion (Investment Promotion Day ) | Not Applicable | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Not Applicable
|  |  | Tourism | 1% | Tourism activities conducted | Number of Tourism activities conducted | 0 | 2 Tourism activities conducted | Not Applicable | Not Applicable | Not Applicable | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Not Applicable
Financial Viability | 5% | To ensure compliance with MFMA and DORA regulations pertaining to reporting by 2022 | Expenditure | 3% | Report on expenditure quartely | % of capital budget spent on capital projects, and % of operational budget spent, measured as the total actual year to date capital expenditure / total approved capital budget x 100 for capital; measured as the total actual year to date operational expenditure / total approved operational budget | 2020/21 capital budget expenditure; 2020/21 operational budget | 100 % of capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100; 100 % of operational budget spent | 10% (Capital); 25% (Operational) | Section 71 Reports Capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100; Operational budget spent | Target not met. Capital Budget expenditure is at 9% and Operational Budget expenditure is at 25%. | Late implementation of projects and infrastructure water crisis. | To liaise with bid committees and user departments on the implementation of projects. | To liaise with bid committees and user departments on the implementation of projects by the end of October 2022. | 40% (Capital) 50% (Operational) | Section 71 Reports Capital budget spent on capital projects, measured as the total actual year to date capital expenditure / total approved capital budget x 100; Operational budget spent. | Target not met. Capital Budget expenditure is at 29% and Operational Budget expenditure is at 48%. | Vacancies had an impact on the expenditure of Compensation of Employees. | HR to speed up filling of vacancies. | The MPAC to sit in the third quarter.
|  |  | Wasteful, irregular and unauthorised | 1% | Reduction of wasteful, irregular and unauthorised expenditure | % reduction on wasteful, irregular and unauthorised expenditure | 0% | 100% reduction on wasteful, irregular and unauthorised expenditure | 25% reduction on wasteful, irregular and unauthorised expenditure | Report | Target not met. | Not Applicable | Not Applicable | Not Applicable | 50% reduction on wasteful, irregular and unauthorised expenditure | Report | Target not met. The irregular expenditure has not been reduced. | Non-functionality of MPAC to consider the irregular expenditure. | Capacity intervention and more support to MPAC by management. | The filling of post will be done in the third quarter.
|  |  | Procurement plans | 1% | Implementation of procurement plans | % progress on the implementation of procurement plans | 0% | 100% progress on the implementation of procurement plans | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 100% progress on the implementation of procurement plans | Report | Target not met.
Good Gov & Public Participation | 80% | To ensure promotion of enterprise – wide risk management processes To strengthen implementation of internal control by 2027 | Risk assessments | 10% | Conduct risk assessement | Number of risk assessments conducted | 1 risk assessments register | 1 risk assessments conducted | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable
|  |  | Risk Register | 10% | Implementation of Risk Register | Number of Reports on the implementation of Risk Register | 1 Reports on the implementation of Risk Register | 4 Reports on the implementation of Risk Register | 1 Reports on the implementation of Risk Register | Report on the implementation of Risk Register | Achieved. Monitored and verified the implementation of risk management treatment plans for Quarter 1. The municipality had 30 treatment plans for the quarter. | Not Applicable | Not Applicable | Not Applicable | 1 Reports on the implementation of Risk Register | Report on the implementation of Risk Register | Target not met. The municipality had 20 treatment plans for the quarter. No verification on the implementation of risk management treatment plans for was done | Not Applicable | Not Applicable | Not Applicable
|  |  | Audit and Performance Committee meeting | 10% | Conduct Audit and Performance Committee meeting | Number of Audit and Performance Committee meetings held on a quarterly basis | 5 Audit and Performance Committee meeting held on a quarterly basis | 4 Audit and Performance Committee meeting held on a quarterly basis | 1 Audit and Performance Committee meeting held on a quarterly basis | Minutes of the Audit and Performance Committee meeting | Achieved. The Audit Committee Meeting was convened in the first quarter of the FY, where the Annual Financial Statements and Annual Performance Report were tabled to the Audit and Performance Audit Committee. | Not Applicable | Not Applicable | Not Applicable | 1 Audit and Performance Committee meeting held on a quarterly basis | Minutes of the Audit and Performance Committee meeting | Target met . The Audit Committee Meeting was convened in October where performance reports and internal reports were tabled. | Not Applicable | Not Applicable | Not Applicable
|  |  | Internal Audit Strategic Risk based Plan | 5% | Develop Internal Audit Strategic Risk based Plan | Number of Internal Audit Strategic Risk based Plans developed and approved by the Audit and Performance Committee for 2022/23 FY | Internal Audit Strategic Risk based Plan | 1 Internal Audit Strategic Risk based Plans developed and approved by the Audit and Performance Committee for 2022/23 FY | Internal Audit Strategic Risk based Plan | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable
|  |  | Internal Audit Plan | 5% | Implementation of the Internal Audit Plan | Number of reports on the implementation of the Internal Audit Plan on a quarterly basis | Report on the implementation of the Internal Audit Plan | 4 reports on the implementation of the Internal Audit Plan on a quarterly basis | 1 report on the implementation of the Internal Audit Plan on a quarterly basis | Report on the implementation of the Internal Audit Plan | Achieved. Monitoring on the implemetation of the Internal Audit plan has been done in the quarter. The Internal Audit Unit had 5 projects/reviews planned for the quarter and they have completed 5. The report on the implementation of Internal Audit Plan has been compiled. | Not Applicable | Not Applicable | Not Applicable | 1 Report on the implementation of the Internal Audit Plan | Report on the implementation of the Internal Audit Plan | Target met. However it must be noted that not all targets were actioned by some directorates (POE report). | The outstanding targets will be actioned in the third quarter. | Not Applicable | Not Applicable
|  |  | Audit and Performance Committee annual oversight report | 5% | Facilitate Audit and Performance Committee annual oversight report | Number of Audit and Performance Committee annual oversight report facilitated | 0 | 1 Audit and Performance Committee annual oversight report facilitated | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 1 Audit and Performance Committee annual oversight report facilitated | Audit and Performance Committee annual oversight report facilitated | Target met. The Audit Committee tabled the oversight report to Council for the 1st Quarter of the FY | Not Applicable | Not Applicable | Not Applicable
|  |  | Audit and Performance Committee and Internal Audit Charters | 5% | Develop Audit and Performance Committee and Internal Audit Charter | Number of Audit and Performance Committee and Internal Audit Charters developed | 1 | 1 Audit and Performance Committee and Internal Audit Charters developed | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable
|  | To ensure that the municipality is responsive to the needs of the community as well as to strengthen a culture of performance management by 2027 and beyond | Intergrated Development Planning | 5% | Review IDP | Number of 2022/27 IDP reviewed | 1 | 2022/27 IDP reviewed | Develop IDP/Budget process plan | IDP/Budget process plan | Target met - IDP/Budget process plan developed and submitted to council for adoption | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable
|  |  | Organisational performance | 5% | Organisational performance assessmnet | No of organisational performance reports | 4 | 4 organisational performance reports | 1 organisational performance reports | organisational performance reports | Target met - 1 organisational performance reports compiled | Not Applicable | Not Applicable | Not Applicable | 1 organisational performance reports | Organisational performance reports | Target met . 1 organisational performance reports tabled to council ( 1st quarter) | Not Applicable | Not Applicable | Not Applicable
|  | Ensure effective, efficient and compliant public participation by 2027 and beyond | Public participation | 5% | Review Public participation strategy | No of Public participation strategy reviewed | Public participation strategy | Review public participation strategy | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Internal consultation on the Public participation strategy | Minutes and attendance register | Target not met - No internal consultation on the Public participation strategy was conducted. | The support that was requested from COGTA for alignment of the strategy was not recived due to the unavailabilty of the department. | The meeting with COGTA will be arranged in Q3 | 2023-03-31
|  |  | Public participation | 5% | Public Participation imbizo | Number of Public Participation sessions held | 10 Public Participation sessions Conducted | 10 Public Participation sessions | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | 5 Public Participation sessions | Minutes and attendance register | Target met - 1 Public participation meeting was held for all wards s per the Mayors advice , due to the community unrest . | Not Applicable | Not Applicable | Not Applicable
|  |  | IGR | 5% | IGR meeting | No of IGR meetings held | 4 IGR meetings held | 4 IGR meetings held | 1 IGR meetings held | Minutes and attendance register | Target met - 1 IGR meeting held | Not Applicable | Not Applicable | Not Applicable | 1 IGR meetings held | Minutes and attendance register | Target not met . IGR meetings was not held. | The preamble towards the sitting of IGR session was the Public Participation meetings for all wards ,however the said meetings could not be held due to community unrest which led to the shutdown of municipal offices. | The meeting will be held in Q3 | 2023-03-31
|  | To ensure mainstreaming of Special Programmes in the institution by 2027 | Social cohesion | 5% | Social cohesion programmes facilitated | No of social cohesion programmes facilitated | 12 social cohesion programmes facilitated | 5 social cohesion programmes facilitated | 1 social cohesion programmes facilitated | Quarterly report and attandance register | Three (3) programmes has been conducted namely; 1)Talent Search/Auditions 2)Women's Day Celebrations. 3)Heritage Day Celebrations. | Not Applicable | Not Applicable | Not Applicable | 2 social cohesion programmes facilitated | Quarterly report and attandance register | Target met. Three (3) programmes has been conducted namely; 1) Business information workshop for Disabled persons. 2) Youth Job Preparation Workshop 3) 16 December 2022 Day of Reconciliation. | Not Applicable | Not Applicable | Not Applicable